## Slide 1: Progress Report Country report of fp2020
Imma Batubara

## Slide 2: OUTLINE
Background and objectives
Report Outline
Summary of Content

## Slide 3: Background
2016 is the fourth year of progress of fulfilling those commitments is a mid point to 2020. A significant period of conducting midterm evaluation towards the work that had been done for the past four years
One of those commitments is to provide annual report to the global secretariat of FP2020.
In October 2015, Indonesia submitted “Progress Achievements toward FP2020 Commitments in Indonesia:
  Description about BKKBN and other stakeholders’ contributions in FP program in Indonesia
Objective of the document:
  To provide information on progress of FP2020 in Indonesia for national and global use
  To opportunity and challenges to way forward to achieve targets (qualitative information through in-depth interview)

## Slide 4: Report Outline
PART 1: INTRODUCTION
  Indonesia: Context of Development
  Overview of Family Program development in Indonesia 1990-2010
PART 2: REVIEW OF MEASURES AT MIDPOINT
  17 core indicators & RPJMN indicators
  Discussion
PART 3: STAKEHOLDERS ANALYSIS ON FP2020 INITIATIVES IN INDONESIA
  FP2020 commitments and its operationalization in Indonesia
  Strength and Weaknesses
PART 4: CONSLUSIONS AND RECOMMENDATIONS (WAY FORWARD)
  Conclusions
  Recommendations

## Slide 5: PART 1: Introduction
Indonesia: Context of Development
  Brief description on the general information of Indonesia
Overview on family planning program in the latest 2 decades:
  The most important milestones of development (decentralization and MDG era where maternal health/FP relatively obtained significant attention)
  Government commitment to revitalize family planning program, FP2020

## Slide 6: PART 2: Review of Measures at Midpoint
BKKBN (Planning unit) has aligned measures from sources to be used for reporting (IDHS 2012, SUPAS 2015, PMA 2015 and SUSENAS 2015)
A policy brief: Indonesia assessing progress toward FP2020 has been produced by Track20 in 2016.
This report used the analyzed data of PMA 2020, policy brief of UGM and Track20,indicator aligned by BKKBN, FP2020 global report, IDHS documents and other publications

## Slide 7: 17 Core Indicators
 | Definition | Current status
1. Additional modern methods users | Number of additional women (or their partners) of reproductive age currently using a modern contraceptive method | 2,214,000 (PMA 2015)
2, mCPR | percentage of women of reproductive age who are using (or whose partner is using) a modern contraceptive method at a particular point in time CPR target (2019): 66% | 45%(AW) (2016, CIC-Track20) CPR: 58.0 (SUPAS 2015) 60.9 (PMA 2015) 60.0 (SUSENAS 2015)
3, Unmet need | percentage of women (or their partners) who desire either to have no additional children or to postpone the next child and who are currently using a modern contraceptive method | 11.4 (IDHS 2012) 13.8 (2016, Track 20) Target RPJMN: 9.9 (2019)
4. % demand satisfied | percentage of women (or their partners) who desire either to have no additional children or to postpone the next child and who are currently using a modern contraceptive method | 79.0 (IDHS 2012) 81.1 (2016, CIC-Track20)

## Slide 8: 17 Core Indicators
 | Definition | Current status
5. Unintended pregnancies | Pregnancies that occurred at a time when women (and their partners) either did not want additional children or wanted to delay the next birth. | 2,607,018 (2016, CIC-Track20)
6. Unintended pregnancies averted | Number of unintended pregnancies that did not occur during a specific reference period as a result of the protection provided by modern contraceptive use during the reference period | 8,148,234 (2016, CIC-Track20)
7. Unsafe abortion averted | Number of unsafe abortion that did not occur during a specified reference period as a result of the protection provided by modern contraceptive use during the reference period. | 2,833,141 (2016, CIC-Track20)
8. Maternal deaths averted | Number of maternal deaths that did not occur during a specified reference period as a result of the protection provided by modern contraceptive use during the reference period. | 14,830 (2016, CIC-Track20)

## Slide 9: 17 Core Indicators
Indicators | Definition | Current status
9. Method mix | Percentage of total family planning users using each modern method of contraception | (See chart) SUPAS (2015), PMA (2015), SUSENAS (2015)
10. % facilities stocked out | Percentage of facilities stocked out, by method offered, on the day of assessment | 17.2* (PMA 2015) only for pill
11. %SDP with method choice | Percentage of Public Facilities that have at least 3 modern methods of contraception Percentage of Public Facilities that have at least 5 modern methods of contraception | See chart PMA (2015)
12. Annual FP expenditures | Total annual public sector recurrent expenditures on FP. This includes expenditures by all level of government | US$533M NIDI (2014)
13.Couple-years of protection (CYP | Estimated protection provided by FP services during a one year period, based upon the volume of all contraceotion sold/distributed free of charges to clients during that period | 48,452,903 (PMA 2015)

## Slide 10: Table 1 Method mix (married women)
Method | SDKI 2012 | SUPAS 2015 | PMA 2015 | SUSENAS 2015
Female Sterilization | 3.2 | 2.5 | 3.8 | 1.9
Male Sterilization | 0.2 | 0.2 | 0.1 | 0.2
IUD | 3.9 | 4.0 | 4.8 | 4.4
Implant | 3.3 | 3.7 | 4.4 | 3.7
Injectables | 31.9 | 33.6 | 31.2 | 35.7
Pills | 13.6 | 12.3 | 13.4 | 12.4
Male Condoms | 1.8 | 0.7 | 1.7 | 0.6
LAM | - | 0.1 | - | 0.1
mCPR | 57.9 | 57.1 | 59.4 | 59.0

## Slide 11: Figure Contraceptives Availability
Percentage of Public Facilities that have at least 3 modern methods of contraception and Percentage of Public Facilities that have at least 5 modern methods of contraception (PMA 2015)
Chart: 
| 3 methods or more | 5 methods or more
Hospital | 94.5 | 81.8
Health centre | 98.1 | 72.8
Sub-Health centre | 75.7 | 28.8
Village Health Post | 73 | 20.3
Delivery Post | 81.8 | 18.2
Total | 90.3 | 60.9

## Slide 12: 17 Core Indicators
Indicators | Definition | Current status
14. Method information index | The extent to which women were given specific information when they received family planning services, It is composed of three questions | 20.8 (PMA 2015)
15. FP information provided by service providers | Percentage of women provided with information on family planning during recent contact with a health service provider | 18.2 (PMA 2015)
16.Female autonomy in FP decision | Percentage of women who decided to use family planning alone or jointly with their husband/partners | 91.5 (PMA 2015)
17. Adolescent birth rate | The number of births to adolescent female aged 15-19 occurring during a given reference period per 1,000 adolescent females | 36 (SUPAS 2015) 48 (PMA 2015) 33 (SUSENAS 2015)

## Slide 13: Discussion
Based on three surveys on 2015 (PMA 2015, SUSENAS 2015, SUPAS2015), CPR of Indonesia projected to be 61.1 in 2020. This is 5 percentage points lower than RPJMN target of 66.3%. Acceleration of program activities is needed to achieve it and fulfill our commitment to global target. With the current state, 1.5% increase of annual increase is needed to achieve the target in 2019
Based on current trajectory, Indonesia should have more than 4 million additional user from 2012 to 2020 to achieve FP2020 target. Potential additional user can be reached by reducing unmeet need, promoting FP program, maintain user and assuring contraceptive commodity available in every SDP.

## Slide 14: PART 3 Stakeholders Perception on FP2020 Initiatives in Indonesia

## Slide 15: Qualitative analysis
In-depth interview was conducted to obtain verify results of the secondary data analysis and obtain more perspectives on the following topics:
  The general present situation of family planning program in Indonesia
  Perspective on FP2020 commitment and progress in Indonesia
  Main challenges and recommendations to move forward
Informants:
  MOH, NGOs, UNFPA, JHU/CCP, WHO, Experts, Youth, religious group representative (some still to be done)

## Slide 16: Knowledge about FP2020 commitment
FP2020 initiative often narrowly associated with FP2020 Country Committee or ICFP
FP2020 commitments and targets are in line with national agenda (RPJMN) and other international commitments (MDGs and SDGs) so essentially it is not a new initiative.
However, as a new commitment as such, FP2020 is not well known by stakeholders, particularly at the local and regional level. Maybe because of the lack of socialization and dissemination about FP2020 commitment
Lack of ownership and unclear leading sector: Is it BKKBN? PMK (Coordinating Minister for Human Development and Culture)? or BAPPENAS ?
The role of other sectors are limited. MOH is considered as “supporting only” and should play a more active role
Informants generally feel that FP2020 commitment has not contributed to significant change in revitalization of FP program in Indonesia  Business as usual

## Slide 17: FP2020 Country Committee
The current FP2020 meetings appear to be more of a knowledge-sharing forum, in which attendees present the work that they are involved in. The country committee has promoted better communication between stakeholders on FP program.
However, there is a need to have more concrete objectives. The focus of a FP2020 Country Committee meeting should address a specific challenge, for example:
  Core indicators of FP2020 have been integrated to strategic roadmap of BKKBN. To get the number of additional user of FP will require modification of forms at the facilities. The follow up meeting should review whether the recommendations have been followed up.
  Lessons learned or work in progress done by stakeholders
  Discussion on FP program in remote areas, supported by further analysis of data
Need to clarify the role of FP2020 Country Committee:“ a pressure group or think tank?”

## Slide 18: Global FP2020 Forum
The global forum is supposed to be a platform for a exchange of lessons learned through regular teleconference. But there is a need to have focused discussion where country of the same interest can learn form other countries. The teleconference should be facilitated by using audio-visual materials.
FP2020 global forum needs be more active in providing lessons learned to countries through various mechanism. Sharing information in the internet is not enough.

## Slide 19: Recommendations
The need to transform FP2020 Country committee into a strategic, problem-solving forum where specific issues are discussed and followed up:
  Acceleration of program to achieve RPJMN and FP2020 commitments
  Forum that facilitate sharing of further analysis of data, example: how to address the need of areas with low FP coverage, the need to have specific intervention, adjust unit cost, etc
  Mechanism to follow up recommendations of the meeting

## Slide 20: THANK YOU